## Bundle Report
JIRA # | Summary | Team | Bundle Status | JIRA Status | Assignee | Reporter | Priority | Sub-Priority | Category | Prioritization Date | HRS/EPM | HRQA/EPQAS Date | PHIRE CR# | CR Type | HRS/EPM Date | Off Bundle Reason | Project Association
HRS-61060 | Developer access to GT eForms Utilites | HRS-Technical | Included in Bundle | Closed | JODI S DUNN | MINDY N HAUKOM | Critical | - | Ops | - | HRS | 2022-08-05 | HRS-CR015149 | Security | 08/22/2022 | - | -
HRS-62931 | Update eBenefits Role for added function-UW_SSC_BN_RECONCILIATION | HRS-HR | Included in Bundle | Closed | VICKI L KISSACK | VICKI L KISSACK | Major | - | Ops | - | HRS | 2022-08-10 | HRS-CR015236 | Config/.dms | 08/22/2022 | - | -
HRS-61831 | Update eBenefits Roles for added functions | HRS-HR | Included in Bundle | Closed | VICKI L KISSACK | TINA SUITER | Major | - | Project | - | HRS | 2022-08-11 | HRS-CR015237 | Security | 08/22/2022 | - | ePfile
HRS-63017 | New WED Report: UW_HR_MISSING_STD_HRS_FREQ | HRS-Payroll | Included in Bundle | Production | MARIA LINDQUIST | MARIA LINDQUIST | Major | - | Project | - | HRS | 2022-08-16 | HRS-CR015241 | Config/.dms | 08/22/2022 | - | -
HRS-61831 | Update eBenefits Roles for added functions | HRS-HR | Included in Bundle | Closed | VICKI L KISSACK | TINA SUITER | Major | - | Project | - | HRS | 2022-08-11 | HRS-CR015243 | Config/.dms | 08/22/2022 | - | ePfile
HRS-60765 | Create Process to Automatically Lock/Unlock PY Pages | HRS-Payroll | Included in Bundle | Closed | MARIA LINDQUIST | KATHRYN M INGRAM | Critical | 3 | Ops | 2022-07-08 | HRS | 2022-08-17 | HRS-CR015244 | Code/Object | 08/22/2022 | - | -
HRS-63104 | UW_BN_IFL_REDUCTION Query Updates | HRS-Benefits | Included in Bundle | Closed | JACK REDELL | JACK REDELL | Major | - | Ops | - | HRS | 2022-08-09 | HRS-CR015249 | Code/Object | 08/22/2022 | - | -
HRS-63100 | PFile - Unable to open electronic file | HRS-HR | Included in Bundle | Closed | ZACK HAAK | ZACK HAAK | Critical | - | Ops | 2022-08-16 | HRS | 2022-08-18 | HRS-CR015259 | Code/Object | 08/22/2022 | - | -
HRS-63106 | Security: Add Page Security for new AE Process to Automatically Lock/UnLock PY Pages | HRS-Payroll | Included in Bundle | Closed | MARIA LINDQUIST | SAJIDA SIDDIQUI | Major | - | Ops | - | HRS | 2022-08-19 | HRS-CR015261 | Security | 08/22/2022 | - | -
HRS-62937 | NACHA - Modify DDUSTRNX To Write Sensitive Files To Encrypted Drive | HRS-Security | Included in Bundle | Closed | MICHAEL G TAYLOR | MICHAEL G TAYLOR | Major | - | Ops | - | HRS | 2022-08-15 | HRS-CR015262 | Code/Object | 08/22/2022 | - | -
HRS-62935 | NACHA - Modify PYGARNSP To Write Sensitive Files To Encrypted Drive | HRS-Security | Included in Bundle | Closed | MICHAEL G TAYLOR | MICHAEL G TAYLOR | Major | - | Ops | - | HRS | 2022-08-15 | HRS-CR015263 | Code/Object | 08/22/2022 | - | -
HRS-62938 | NACHA - Modify UWPYB006 To Write Sensitive Files To Encrypted Drive | HRS-Security | Included in Bundle | Closed | MICHAEL G TAYLOR | MICHAEL G TAYLOR | Major | - | Ops | - | HRS | 2022-08-15 | HRS-CR015264 | Code/Object | 08/22/2022 | - | -
HRS-63118 | HR - Updates To TTC Job Codes v16 | HRS-HR | Included in Bundle | Closed | THOMAS OATMAN | THOMAS OATMAN | Critical | - | Project | 2022-08-09 | HRS | 2022-08-16 | HRS-CR015268 | Config/.dms | 08/22/2022 | - | Title & Total Compensation
HRS-63119 | HR - Updates To TTC Job Profiles v16 | HRS-HR | Included in Bundle | Closed | THOMAS OATMAN | THOMAS OATMAN | Critical | - | Project | 2022-08-09 | HRS | 2022-08-16 | HRS-CR015270 | Config/.dms | 08/22/2022 | - | Title & Total Compensation
HRS-63120 | HR - Updates To TTC Salary Structure v17 | HRS-HR | Included in Bundle | Closed | THOMAS OATMAN | THOMAS OATMAN | Critical | - | Project | 2022-08-09 | HRS | 2022-08-16 | HRS-CR015272 | Config/.dms | 08/22/2022 | - | Title & Total Compensation
HRS-63142 | BN - HRS Title & Total Compensation Job Code Enhancements #17 | HRS-Benefits | Included in Bundle | Closed | ERINN KATHLEEN BITTINGER-PULLEN | ERINN KATHLEEN BITTINGER-PULLEN | Major | - | Ops | - | HRS | 2022-08-16 | HRS-CR015273 | Config/.dms | 08/22/2022 | - | -
HRS-62834 | New & Updated Time & Labor Public Queries | HRS-Time & Labor | Off-bundle | Closed | NEAL A WERMUTH | NEAL A WERMUTH | Major | - | Ops | - | HRS | 2022-07-11 | HRS-CR015150 | Code/Object | 08/09/2022 | No Regression Test needed | -
HRS-63021 | Dev Retrofits of Oracle July 2022 CPU (pTools 8.58.20) | HRS-Technical | Off-bundle | Closed | Team: HRS Testing | JODI S DUNN | Critical | - | Project | 2022-07-28 | HRS | 2022-08-08 | HRS-CR015223 | Code/Object | 08/21/2022 | Other | Quarterly - Oracle Patching Q3
HRS-63198 | Deduction distribution adjustments for single payment checks V3 | HRS-Financials | Off-bundle | Regression Test | BRAD BRUEGGER | BRAD BRUEGGER | Critical | - | Ops | - | HRS | 2022-08-29 | HRS-CR015247 | Code/Object | 08/18/2022 | - | -
HRS-63198 | Deduction distribution adjustments for single payment checks V3 | HRS-Financials | Off-bundle | Regression Test | BRAD BRUEGGER | BRAD BRUEGGER | Critical | - | Ops | - | HRS | 2022-08-29 | HRS-CR015247 | Code/Object | 08/19/2022 | - | -
HRS-62687 | NORPT Flag not going to zero with middle of pay period LOA | HRS-Absence management | Off-bundle | Closed | CHRISTINE PELO | CHRISTINE PELO | Major | - | Ops | 2022-06-13 | HRS | 2022-08-09 | HRS-CR015250 | Config/.dms | 08/09/2022 | Critical Business Deadline | -
HRS-63155 | Issues running files 21 and 22 from HRS - Export Demographics to Glacier | HRS-Payroll | Off-bundle | Closed | TERI VAN GENDEREN | TERI VAN GENDEREN | Blocker | - | Ops | - | HRS | 2022-08-17 | HRS-CR015274 | Code/Object | 08/17/2022 | Critical Business Deadline | -
HRS-63191 | Deduction distribution adjustments for single payment checks V2 | HRS-Financials | Off-bundle | Production | BRAD BRUEGGER | BRAD BRUEGGER | Critical | - | Ops | - | HRS | 2022-08-19 | HRS-CR015284 | Code/Object | 08/19/2022 | - | -
HRS-63191 | Deduction distribution adjustments for single payment checks V2 | HRS-Financials | Off-bundle | Production | BRAD BRUEGGER | BRAD BRUEGGER | Critical | - | Ops | - | HRS | 2022-08-19 | HRS-CR015284 | Code/Object | 08/19/2022 | - | -
HRS-63116 | HRTRN: Restore Finance / Budget Tables that Reflect Current FY Data | HRS-Financials | Off-bundle | Regression Test | MARIA LINDQUIST | MARIA LINDQUIST | Major | - | Ops | - | HRS | - | HRS-CR015253 | Config/.dms | 08/09/2022 | - | -
HRS-63147 | UWMSN Fiscal Year 2023 Organizational Department Request- (Add) | HRS-HR | Org Dept Update | Closed | JULIE PANKE | JULIE PANKE | Critical | 1 | Ops | 2022-08-15 | HRS | N/A | N/A - No PHIRE CR | N/A (Configuration) | 2022-08-18 | - | -
HRS-63136 | UWGBY Fiscal Year 2023 Organizational Department Request- (Add) | HRS-HR | Org Dept Update | Closed | JULIE PANKE | JULIE PANKE | Critical | 1 | Ops | 2022-08-15 | HRS | N/A | N/A - No PHIRE CR | N/A (Configuration) | 2022-08-17 | - | -
HRS-63138 | UWMSN Fiscal Year 2023 Organizational Department Request- (Add) | HRS-HR | Org Dept Update | Closed | JULIE PANKE | JULIE PANKE | Critical | 1 | Ops | 2022-08-12 | HRS | N/A | N/A - No PHIRE CR | N/A (Configuration) | 2022-08-16 | - | -
HRS-63131 | UWMSN Fiscal Year 2023 Organizational Department Request- (Add) | HRS-HR | Org Dept Update | Closed | JULIE PANKE | JULIE PANKE | Critical | 1 | Ops | 2022-08-11 | HRS | N/A | N/A - No PHIRE CR | N/A (Configuration) | 2022-08-16 | - | -
HRS-59746 | UWMSN Fiscal Year 2022 Organizational Department Request- (Add & Change) | HRS-HR | Org Dept Update | Closed | JULIE PANKE | JULIE PANKE | Critical | 1 | Ops | 2021-05-27 | HRS | N/A | N/A - No PHIRE CR | N/A (Configuration) | 2022-08-15 | - | -
HRS-63114 | Time & Labor Exception Audit & Cleanup | HRS-Time & Labor | Data Update | Closed | NEAL A WERMUTH | NEAL A WERMUTH | Critical | - | Ops | - | HRS | - | HRS-CR015251 | Data Update/SQL | 08/09/2022 | - | -
HRS-63123 | Payable Time 'NA' and 'RP' Status Cleanup | HRS-Time & Labor | Data Update | Closed | NEAL A WERMUTH | NEAL A WERMUTH | Critical | - | Ops | - | HRS | - | HRS-CR015255 | Data Update/SQL | 08/10/2022 | - | -
HRS-63133 | 2022BW08A SQL Update for Job Code Errors | HRS-Financials | Data Update | Closed | KELSEY ELISE LAAGER | KELSEY ELISE LAAGER | Major | - | Ops | - | HRS | - | HRS-CR015260 | Data Update/SQL | 08/18/2022 | - | -
HRS-63140 | UW_AM_RTPSHP Preventative Maintenance 08A - Unique Constraint - Delete rows from PS_UW_AM_PY_SNT_RT | HRS-Absence management | Data Update | Closed | QUIN KNUTESON | QUIN KNUTESON | Major | - | Ops | - | HRS | - | HRS-CR015265 | Data Update/SQL | 08/15/2022 | - | -
HRS-63156 | Update PAY_CALENDAR for Old Pay Group for former UNC07, 8A | HRS-Financials | Data Update | Closed | JESSICA RASMUSSEN | ZACK HAAK | Major | - | Ops | - | HRS | - | HRS-CR015278 | Data Update/SQL | 08/19/2022 | - | -

## Phire Audit
Phire CR Number | JIRA Tracking # | Target DB | Migrated On | Migrated By | CR Type | Query
CR015149 | HRS-61060 | HRS | 08/22/2022 4:34:06PM | 00274593 | SCRT | UW_MIGR_HISTORY_AUDIT_LAB
CR015150 | HRS-62834 | HRS | 08/09/2022 4:17:46PM | 00274593 | CODE | UW_MIGR_HISTORY_AUDIT_LAB
CR015223 | HRS-63021 | HRS | 08/21/2022 9:34:37AM | 00274593 | CODE | UW_MIGR_HISTORY_AUDIT_LAB
CR015236 | HRS-62931 | HRS | 08/22/2022 4:31:08PM | 00274593 | SCRP | UW_MIGR_HISTORY_AUDIT_LAB
CR015237 | HRS-61831 | HRS | 08/22/2022 4:34:51PM | 00274593 | SCRT | UW_MIGR_HISTORY_AUDIT_LAB
CR015241 | HRS-63017 | HRS | 08/22/2022 4:31:32PM | 00274593 | SCRP | UW_MIGR_HISTORY_AUDIT_LAB
CR015243 | HRS-61831 | HRS | 08/22/2022 4:31:04PM | 00274593 | SCRP | UW_MIGR_HISTORY_AUDIT_LAB
CR015244 | HRS-60765 | HRS | 08/22/2022 4:31:00PM | 00274593 | CODE | UW_MIGR_HISTORY_AUDIT_LAB
CR015247 | HRS-63198 | HRS | 08/18/2022 8:30:43AM | 00150774 | CODE | UW_MIGR_HISTORY_AUDIT_LAB
CR015247 | HRS-63198 | HRS | 08/19/2022 8:38:01AM | 00274593 | CODE | UW_MIGR_HISTORY_AUDIT_LAB
CR015249 | HRS-63104 | HRS | 08/22/2022 4:31:54PM | 00274593 | CODE | UW_MIGR_HISTORY_AUDIT_LAB
CR015250 | HRS-62687 | HRS | 08/09/2022 4:44:36PM | 00274593 | SCRP | UW_MIGR_HISTORY_AUDIT_LAB
CR015251 | HRS-63114 | HRS | 08/09/2022 8:11:35AM | 00150774 | HFIX | UW_MIGR_HISTORY_AUDIT_LAB
CR015255 | HRS-63123 | HRS | 08/10/2022 4:18:35PM | 00274593 | HFIX | UW_MIGR_HISTORY_AUDIT_LAB
CR015259 | HRS-63100 | HRS | 08/22/2022 4:31:48PM | 00274593 | CODE | UW_MIGR_HISTORY_AUDIT_LAB
CR015260 | HRS-63133 | HRS | 08/18/2022 3:27:41PM | 00181906 | HFIX | UW_MIGR_HISTORY_AUDIT_LAB
CR015261 | HRS-63106 | HRS | 08/22/2022 4:35:40PM | 00274593 | SCRT | UW_MIGR_HISTORY_AUDIT_LAB
CR015262 | HRS-62937 | HRS | 08/22/2022 4:31:24PM | 00274593 | CODE | UW_MIGR_HISTORY_AUDIT_LAB
CR015263 | HRS-62935 | HRS | 08/22/2022 4:31:13PM | 00274593 | CODE | UW_MIGR_HISTORY_AUDIT_LAB
CR015264 | HRS-62938 | HRS | 08/22/2022 4:31:29PM | 00274593 | CODE | UW_MIGR_HISTORY_AUDIT_LAB
CR015265 | HRS-63140 | HRS | 08/15/2022 9:29:42AM | 00150774 | HFIX | UW_MIGR_HISTORY_AUDIT_LAB
CR015268 | HRS-63118 | HRS | 08/22/2022 4:31:58PM | 00274593 | SCRP | UW_MIGR_HISTORY_AUDIT_LAB
CR015270 | HRS-63119 | HRS | 08/22/2022 4:32:03PM | 00274593 | SCRP | UW_MIGR_HISTORY_AUDIT_LAB
CR015272 | HRS-63120 | HRS | 08/22/2022 4:32:30PM | 00274593 | SCRP | UW_MIGR_HISTORY_AUDIT_LAB
CR015273 | HRS-63142 | HRS | 08/22/2022 4:33:24PM | 00274593 | SCRP | UW_MIGR_HISTORY_AUDIT_LAB
CR015274 | HRS-63155 | HRS | 08/17/2022 3:23:44PM | 00274593 | CODE | UW_MIGR_HISTORY_AUDIT_LAB
CR015278 | HRS-63156 | HRS | 08/19/2022 4:15:59PM | 00181906 | HFIX | UW_MIGR_HISTORY_AUDIT_LAB
CR015284 | HRS-63191 | HRS | 08/19/2022 2:29:14AM | 00274593 | CODE | UW_MIGR_HISTORY_AUDIT_LAB
CR015284 | HRS-63191 | HRS | 08/19/2022 8:36:24AM | 00274593 | CODE | UW_MIGR_HISTORY_AUDIT_LAB
CR015253 | HRS-63116 | HRS | 08/09/2022 12:40:23PM | 00150774 | SCRP | UW_SQL_HISTORY_AUDIT_LAB
N/A - No PHIRE CR | HRS-63147 | HRS | 2022-08-18 10:11:25 | N/A | N/A | ORG_DEPT_UPDATE
N/A - No PHIRE CR | HRS-63136 | HRS | 2022-08-17 11:58:10 | N/A | N/A | ORG_DEPT_UPDATE
N/A - No PHIRE CR | HRS-63138 | HRS | 2022-08-16 14:57:37 | N/A | N/A | ORG_DEPT_UPDATE
N/A - No PHIRE CR | HRS-63131 | HRS | 2022-08-16 07:42:22 | N/A | N/A | ORG_DEPT_UPDATE
N/A - No PHIRE CR | HRS-59746 | HRS | 2022-08-15 15:10:38 | N/A | N/A | ORG_DEPT_UPDATE